I would treat this as a change program, not a tech program. For a department of about 100 people, the goal is not to build a huge AI team; it is to create a small, credible hub that helps the rest of the department use AI safely and effectively.

My approach would be:

1. Define the purpose very clearly
The center of excellence should answer three questions:

- What problems are we solving with AI?

- What guardrails do people need?

- How do we turn good ideas into real use cases?

A useful CoE mission could be:
“Enable the department to identify, test, and scale AI use cases that improve productivity, quality, and decision-making.”

2. Start with a light operating model
For a department your size, I would not create a big formal structure. I would set up:

- One owner: you or a designated AI lead

- A small core group: 3–5 people with different strengths, for example business, data/tech, risk/compliance, and operations

- AI champions in different sub-teams who can spot opportunities and spread adoption

This keeps it lean while still giving the effort structure.

3. Focus on use cases, not tools
The biggest mistake is starting with “Which AI platform should we buy?” instead of “Where is the pain?”

I would run a short use-case discovery process and score ideas based on:

- business value

- feasibility

- risk

- time to implement

Good early use cases are usually things like:

- drafting and summarizing documents

- searching internal knowledge faster

- meeting notes and action extraction

- classifying or routing incoming requests

- first-pass analysis or reporting

- support for repetitive internal workflows

For the first wave, choose 2–3 low-risk, high-visibility use cases that can show value within 6–12 weeks.

4. Put governance in place early
Even in a small department, people need clarity on what is allowed.

At minimum, define:

- what data can and cannot be used with AI tools

- which tools are approved

- who reviews higher-risk use cases

- rules for human review before output is used externally

- how to handle privacy, security, and IP concerns

This does not need to be heavy, but it must be clear. If the rules are vague, adoption will stall.

5. Build an intake and prioritization process
Make it easy for people to bring ideas to the CoE.

A simple intake form can ask:

- what problem are you trying to solve?

- who is affected?

- what data is involved?

- what is the expected benefit?

- what happens if we do nothing?

Then the CoE can decide:

- do not pursue

- pilot

- scale

This prevents the CoE from becoming a random idea inbox.

6. Create a repeatable pilot model
Each pilot should have the same basic structure:

- problem statement

- owner

- success metric

- risk check

- pilot scope

- timeline

- decision at the end: stop, iterate, or scale

That discipline matters. It keeps the CoE from becoming a collection of interesting experiments with no business impact.

7. Measure impact in business language
Do not measure success mainly by “number of AI workshops held.” Measure:

- hours saved

- cycle time reduced

- quality improvements

- adoption rate

- user satisfaction

- number of scaled use cases

For leadership, this is what makes the CoE credible.

8. Invest heavily in capability building
A CoE is also an education engine. In a 100-person department, many people do not need to become AI experts, but they do need enough literacy to use tools well and safely.

I would run training in three levels:

- All employees: basic AI literacy, safe usage, prompting basics

- Champions/managers: identifying use cases, reviewing outputs, change management

- Core team: governance, use case design, evaluation, vendor/tool understanding

9. Communicate progress visibly
People need to see that this is real. I would create a simple internal presence:

- a short page explaining the CoE

- approved tools and policies

- a list of active pilots

- a few examples of wins

- contact points for ideas and support

Visibility creates pull.

10. Build for scale only after the first wins
Once the first pilots prove value, expand by:

- documenting reusable patterns and prompts

- standardizing workflows

- creating templates

- integrating AI into existing processes

- moving from experimentation to ownership in the line organization

The CoE should eventually become a capability enabler, not the place where all AI work lives forever.

A simple way to think about the first 90 days:

First 30 days: map priorities, stakeholders, and risks
Days 31–60: identify and select first pilots, define governance
Days 61–90: launch pilots, train champions, measure early impact

If I were doing this in your situation, I would keep it deliberately small at the beginning: one lead, a few champions, a clear intake process, a couple of pilots, and a very practical governance model. That is enough to create momentum without overengineering it.